## Sheet1
Duty of Care Task Force: Implementation M&E Dashboard
|  | Yes | implemented
|  | No | not implemented currently
|  | In progress | ongoing implementation
|  | NA | Not applicable
|  |  | UN Secretariat | ILO | FAO | UNESCO | UNAIDS | ICAO | WHO | World Bank | IMF | UPU | ITU | WMO | IMO | WIPO | IFAD | UNIDO | UN WTO | IAEA | IOM | UNCTAD | UNDP | UNEP | UNHCR | UNRWA | UNICEF | UNFPA | WFP | UNOV/UNODC | UN HABITAT | UN WOMEN | UNOPS
Pre-deployment guide The Task Force asks the HLCM to adopt the comprehensive pre-deployment guide, including the resilience briefing, as a standard. (Adoption 1) | Each organization to embed the guide in their pre-deployment induction starting May 2018. (Action 1.a.) | Number of organizations that provide a pre-deployment guide to personnel as part of the induction.
Number of organizations that provide resilience briefings to all personnel deployed to high-risk locations.
| Each Country Team is provided with information on the minimum elements that need to be included in the country specific fact sheet. | Country Teams have been provided the minimum elements that need to be included in the country specific fact sheets.
| Each Country Team under the leadership of the RC to ensure that the country-specific fact sheet is updated annually (or more frequently if the risk environment changes). (Action 1.b.) | Number of Country Teams in high-risk duty stations that have developed the country-specific factsheet and made it available to all personnel.
Number of Country Teams that have updated their country-specific factsheet annually (or more frequently if the risk environment has changed) and made it available to all personnel.
Training for Managers The Task Force asks the HLCM to agree that the work on additional content for the training for managers continues in the next phase of the Task Force. (Adoption 2) | Continue to develop the training materials for managers in high-risk locations. | Additional content for the management training (for all personnel) is developed and endorsed by the HLCM.
The mechanism(s) for disseminating the training material has been established in organizations.
| Organization to put in place mechanisms to provide continuous support to managers who are serving in high-risk environments, as per Training Programme for Managers in High-Risk Environments (Annex 6). (Action 2) | Number of organizations that have incorporated inter-agency content in existing support/training for managers in high-risk environments.
Health Risk Assessment and Health Support Planning Following adoption by HLCM in September 2017 of the Duty Station Health Risk Assessment Methodology and Tools, the Task Force asks the HLCM to adopt the Referral Hospital Assessment Manual as a standard for the UN. (Adoption 3) | UNMD to continue the health risk assessments with focus on high-risk duty stations in Afghanistan, Cameroon, Central African Republic, Chad, Ethiopia, Iraq, Kenya, Libya, Mali, Niger, Nigeria, Pakistan, Sudan, Syria and complete by end of 2020. (Action 3.a.) | Number of DS-HRA completed in all 18 high-risk environments.
| *DS-HRA was already conducted in four high-risk duty stations (DRC, South Sudan, Somalia, Yemen). | Findings of the DS-HRA for all 18 high-risk environments are made available to organizations.
| Each UN Country Team is informed of the outcome of the Duty Station Health Risk Assessment and the recommendations for Health Support Plans[1]. | Number of Country Teams informed of the outcome.
| UN Country Team, under the supervision of the Resident Coordinator, to implement the Health Support Plan based on the recommendations provided by UNMD following the Duty Station Health Risk Assessment. | Status report on the implementation of the Health Support Plan. The report should indicate whether the Health Support Plan are implemented fully, partially or not implemented and include foreseen impact of the (non)implementation.
| Organizations should establish a process for their Country Offices to request support to implement the measures in the health support plan within the recommended timelines. Measures which cannot be implemented should be included in the Duty of Care risk management framework. (Action 3.b.) | Number of organizations that have a process for Country Offices to request and receive support to implement the health support plans.
Number of UNCTs/countries that have implemented the health support plans within the recommended timelines.
Streamlining insurance processing mechanism The Task Force asks the HLCM to adopt online claiming for medical insurance as a standard. (Adoption 4) The Task Force asks the HLCM to adopt the principle that, in any duty station, administrative measures should be devised to allow personnel to receive the necessary medical services from any type of UN clinic, including DPKO clinics. (Adoption 5) The Task Force asks the HLCM to adopt measures to ensure that payments to beneficiaries are made within 60 days of receipt of all documents, as a minimum standard. (Adoption 6) | Organizations to implement online claiming for medical insurance. (Action 4) | Number of organizations that have implemented online claiming for medical insurance for staff.
| Organizations governed by the UN Staff Regulations and Rules are to improve communication to staff with regards to Appendix D claims processing, by ensuring that the revised Appendix D, manager’s guide and the online form are made available in the organization’s intranet site. (Action 5.a.) | Number of organizations that have made information on the revised Appendix D, manager’s guide and the online forms available on the organization’s intranet.
| Organizations appoint an Appendix D focal point and make their name and contact details available on the intranet site. (Action 5.b.) | Number of organizations that have appointed an Appendix D focal point and made their names and contact information available on the organization’s intranet.
| Ensure payments to beneficiaries are made within 60 days of receipt of all documents. | Percentage of payments to beneficiaries that are made within 60 days of receipt of all documents by organization.
| Organizations to devise measures (e.g. establish agreements/MoUs with clinics, streamline insurance plans etc.) to allow personnel to receive medical services from any type of UN clinics, including DPKO clinics. | Number of organizations that have developed administrative measures to allow all personnel to receive the necessary medical services from any type of UN clinics, including DPKO clinics.
| Organizations ensure effective measures to assist staff to update their beneficiaries form as applicable. (Action 6.a.). | Number of organizations which have developed measures and/or communication efforts to assist staff to update their beneficiaries forms.
| Organizations to establish an internal process on claiming for compensation under the Malicious Act Insurance Policy. (Action 6.b.) | Number of organizations that have established internal processes on claiming for MAIP compensation.
| Organizations to have an internal process to verify the insurance coverage of non-staff personnel, prior to deployment to high-risk environment. (Action 7) | Number of organizations that established a process to verify that non-staff personnel have insurance coverage prior to deployment to high-risk environment.
UN living and working standards The Task Force asks the HLCM to adopt the UN minimum working and living standards. (Adoption 7) | Ensure UN minimum working and living conditions are adopted as a standard. | Number of organizations that have policies, procedures or guidance reflecting UN minimum working and living conditions for all personnel endorsed by the HLCM
| All new accommodations and office premises are built based on the minimum standards. (Action 8.a.) | Number of organizations that are implementing UN minimum living and working conditions for their new accommodations and office premises in high-risk environments.
| Existing accommodations and office premises are retrofitted/renovated to bring into compliance with UN minimum working and living standards, as applicable. Regular monitoring of the status of working and living standards. (Action 8.b., 8.c.) | Number of organizations which have established a plan to renovate existing accommodations/office premises to bring into compliance with UN minimum working and living conditions.
Number of organizations that are monitoring the status of working and living conditions in high-risk duty stations on at least an annual basis.
| Mechanisms and tools are developed to facilitate implementation of UN minimum working and living standards in organizations. | Specific mechanisms and tools that are developed to facilitate implementation of UN minimum working and living conditions in organizations.
Ensuring adequate bandwidth Adopted the principle that personnel in high-risk environments should have adequate bandwidth to connect with their families and for tele-health services, as per parameters provided in Annex 12. (Adoption 8) | Existing accommodations and office premises are brought into compliance with bandwidth parameters provided in Annex 12. Regular monitoring of the status of bandwidth for personal and tele-health services for all personnel. (Action 9.a., 9.b.) | Number of organizations which have established a plan to bring existing accommodations/office premises in compliance with bandwidth requirements for all personnel.
Number of organizations that are monitoring the status of bandwidth in the duty station for personal and tele-health services on at least an annual basis.
Mental Health Strategy | UN Mental Health Strategy is implemented (Strategy adopted in September 2017). | The implementation strategy is developed and endorsed by the HRN for submission to HLCM (Oct 2018).
A team dedicated to work on the implementation of the Mental Health Strategy led by the P5 is established.
The governance structure defining the reporting line vis-à-vis the HLCM, HR Network, UNMD and the Duty of Care Task Force is established.
Number of organizations that have adopted and have begun implementation of the Mental Health Strategy.
Medical travel The Task Force asks the HLCM to adopt access to essential health services as a standard for UN personnel. (Adoption 9) | Organizations to review their policy on medical evacuation in light of this principle and conduct the necessary actuarial studies to make decisions. (Action 10.a.) | Number of organizations that have conducted the necessary actuarial studies to make decisions.
Number of organizations that have established or revised policies regarding medical travel for staff and families to secure essential medical care for chronic medical conditions requiring medical intervention that is unavailable or inadequate in the duty station.
| Regional area of care (RAC) Committee to formalize Terms of Reference and standard operating procedures, in consultation with the Duty of Care Task Force. (Action 10.b.) | The Terms of Reference and SOPs are developed by the RAC Committee.
Locally-recruited staff: Residential safety and security The Task Force asks the HLCM to adopt the principle that, as part of the security management process, the SMT in high-risk environments should review and advise the Designated Official if additional security measures for locally-recruited staff are required. (Adoption 10) | Organizations should make the necessary administrative and financial support available to Country Representatives where the Designated Official has made decisions to provide additional security measures for locally-recruited staff. (Action 11) | Number of organizations that have established a mechanism to provide administrative and financial support to their Country Representatives to provide additional residential safety and security measures for locally-recruited staff upon SMT recommendation.
Locally-recruited staff: Compressed time-off The Task Force asks the HLCM to adopt, as a standard, where it is feasible, to allow locally-recruited staff in high-risk environments to accumulate up to 5 working days of their compressed time-off to be taken consecutively. (Adoption 11) | Agree on an inter-agency compressed time off schedule with a view toward aligning schedules between organizations. (Action 12) | Organizations have established a common inter-agency compressed time-off schedule for locally-recruited staff.
Locally-recruited staff: Affordable and safe transportation The Task Force asks the HLCM to adopt, as a standard, safe transportation from residence to office for locally-recruited staff, subject to the local security condition, as advised by SMT. (Adoption 12) | Organizations to make the necessary administrative and financial support available to their Country Representative where SMT has made decisions to provide additional measures for locally-recruited staff. (Action 13) | Number of organizations that have established a mechanism to provide administrative and financial support to their Country Representatives to enable them to provide additional measures to ensure safe transportation for locally-recruited staff upon SMT recommendation.
First-aid and medical essentials kit | Provide the necessary first-aid and medical essentials as per Medical Services and/or SMT recommendation. (Action 14) | Number of organizations that provide first-aid and medical essential kits in high-risk environments as per Medical Services and/or SMT recommendation.
Duty of Care: non-staff Review the Duty of Care for non-staff personnel | Review and develop measures to provide Duty of Care to non-staff personnel (e.g. UN Volunteers, individual contractors, consultants, interns, fellows, standby personnel, etc.). Review the measures based on the different contractual status. | Measures developed and endorsed by HR Network members
[1] Italicized items were added following consultation with the relevant stakeholders, after the circulation of the framework to HLCM members on 24 August 2018.